## Overview
Labour Case Management Web App — Development Master Plan (v2)
Fresh build, inspired by tapace.com, for case notices + automated party notifications
Item | Detail
Version | v2 — revised 27 Sep 2026 after plan review. Original kept as Labour_Portal_Full_Development_Plan_v1_backup.xlsx
Purpose | Internal web app to manage Labour Department case files (EC/ID/S&E/etc.), track hearings, generate notices, and auto-notify both applicant and management by Email + WhatsApp
Frontend | Next.js, hosted on Vercel
Backend / Database | Supabase — Postgres database, Auth (login/roles), Storage (private bucket for uploaded docs & generated notices, shared via expiring signed URLs)
Automation | Make.com — three scenarios: (1) Immediate notify on notice creation, (2) Daily scheduled notify for upcoming hearings, (3) Retry of failed deliveries. Every send is recorded per party + channel in notice_deliveries
Notification channels | Email and WhatsApp (WhatsApp requires a Business API provider such as Gupshup / 360dialog / Twilio, Meta business verification, and pre-approved message templates — long lead time, start in Week 0)
Reference UI | tapace.com screens: Form Details, Receive Management, Section Management, Staff Management, Advanced Filters, Create Current Entry
Core users | Admin (full access) and Staff/Officers (assigned cases only) via role-based access. Role names everywhere: admin / staff
Open decisions | 1) Can staff see their own slice of the Monthly MIS? 2) Are notices bilingual (Telugu + English)? 3) Is file_number unique per office (multi-office) or statewide? 4) PDF output needed, or DOCX only? 5) Owners for each Roadmap task
How to use this file | Roadmap tab = week-by-week build plan (Week 0 pre-work first) · Screens tab = every page to build · Data Model tab = database tables · RBAC tab = who can do what · Automation tab = Make.com scenarios & rules · Setup Checklist = one-time setup steps · Change Log = what changed from v1 and why

## Roadmap
Development Roadmap (v2)
Week 0 pre-work + 10-week build. Row colours: green = NEW in v2 · yellow = CHANGED/MOVED · red strikethrough = REMOVED (see Change Log tab)
Phase | Week | Task | Description | Tech/Tool | Deliverable | Owner | Status | Notes | v2 Change
Phase 0: Pre-work (start now) | Week 0 | WhatsApp provider & Meta verification | Sign up with provider (Gupshup / 360dialog / Twilio), complete Meta Business verification for the department | WhatsApp Business API | Verified WhatsApp sender number |  | Not started | Long lead time (days–weeks); blocks Week 6 | NEW — was only a checklist item
| Week 0 | WhatsApp message template approval | Draft & submit hearing / show-cause / closure / order templates with document header for Meta approval | WhatsApp Business API | Approved template names |  | Not started | Business-initiated messages outside 24h window must use approved templates | NEW
| Week 0 | Notice templates & language | Finalise letterhead + wording for every notice type; decide Telugu/English | Word / Google Docs | Signed-off DOCX templates |  | Not started | Blocks Week 5 template engine | MOVED from Setup Checklist item 8
| Week 0 | Data migration scoping | Export existing cases from tapace.com / Excel; map old columns to new schema; list data-quality issues | Excel | Column mapping sheet + sample export |  | Not started | Needed so schema covers real data | NEW
Phase 1: Foundation | Week 1 | Project setup | Initialize Next.js app, connect to Vercel, set up Supabase project | Next.js, Vercel, Supabase | Deployed skeleton app on Vercel |  | Not started | Create separate dev/prod Supabase projects
| Week 1 | Auth & profiles | Supabase Auth (email/magic link), profiles table with role (admin/staff), active flag | Supabase Auth | Login working, roles stored |  | Not started | RLS policies moved to Week 2 (need cases table) | CHANGED — RLS split out
| Week 2 | Core database schema (v2) | Tables: cases, parties, hearings, sections, received_from, profiles, case_status_history, audit_log | Supabase Postgres | Schema deployed with relationships |  | Not started | See Data Model tab (v2) | CHANGED — added hearings, history, audit
| Week 2 | RLS policies + tests | Admin sees all; staff only assigned cases. Policies on child tables (parties, hearings, notices, remarks) join to cases. Staff-created case auto-assigned to creator | Supabase RLS | Automated RLS tests passing |  | Not started | Tested from day one, not only at Week 8 | MOVED from Week 1 + NEW tests
| Week 2 | Admin lookup management | CRUD UI for Sections and Received-From lists | Next.js, Supabase | Section & Receive Management screens |  | Not started | Matches existing tapace.com pattern
Phase 2: Case Management | Week 3 | Case CRUD | Create/view/edit case: file number, act, dates, status, subject. Soft delete (deleted_at). Status change writes case_status_history + closed_at | Next.js, Supabase | Case list + case detail page |  | Not started |  | CHANGED — soft delete, status history
| Week 3 | Applicant & Management details | Sub-forms for both parties: name, phone(s), WhatsApp number, email, address | Next.js, Supabase | Parties linked to case |  | Not started | Validate WhatsApp number in +91 format | CHANGED — whatsapp_phone
| Week 4 | Hearings | Schedule / reschedule / mark held or adjourned; hearing history on case page; cases.next_hearing_date kept in sync | Next.js, Supabase | Hearing history per case |  | Not started |  | NEW
| Week 4 | Filters & search | Filter by file number, act, section, receive-from, hearing date range | Next.js, Supabase | Advanced Filters screen |  | Not started
| Week 4 | Dashboard stats | Act/Section-wise Total/Closed/Open/Forwarded counts | Supabase views/RPC | Stats dashboard per Act/Section |  | Not started
Phase 3: Notices & Documents | Week 5 | DOCX template engine | Templated notice/order generation from case + hearing data | docxtemplater, Supabase Storage | Print Notice / Download DOCX feature |  | Not started | PDF: LibreOffice not available on Vercel — use a conversion service or ship DOCX only | CHANGED — PDF risk noted
| Week 5 | Notice tables & storage | notices, notice_deliveries, notice_templates tables; private storage bucket; signed URLs with expiry | Supabase Postgres, Storage | Notice + per-party/channel delivery history |  | Not started |  | CHANGED — per-delivery tracking
| Week 6 | Notice generation API route | Builds doc, uploads to Storage, creates notice + 4 pending deliveries, fires webhook with shared secret + idempotency key | Next.js API route / Edge Function | Working generate-and-notify endpoint |  | Not started | Payload: notice_id, case_id, hearing_id, parties, signed doc_url, template names | CHANGED — secret + idempotency
Phase 4: Automation (Make.com) | Week 6 | Immediate notify scenario | Webhook-triggered: verify secret, Email + WhatsApp to both parties, write back each delivery | Make.com, Email, WhatsApp Business API | Scenario 1 live and tested |  | Not started | Needs approved WhatsApp templates from Week 0
| Week 7 | Batch notify scenario | Daily: fetch hearings in next N days with no delivered notice for that hearing; generate notice via API route, then send | Make.com scheduler, Supabase Edge Function | Scenario 2 live and tested |  | Not started | Dedupe by (hearing_id, notice type) so Scenario 1 + 2 never double-send | CHANGED — dedupe + generates notice
| Week 7 | Delivery status writeback | Make.com updates notice_deliveries (status, provider_message_id, error); notices.status rolls up | Make.com HTTP module, Supabase REST API | Sent/Delivered/Failed per party & channel |  | Not started | Provider message IDs kept as proof of service | CHANGED — per delivery
| Week 8 | Failed delivery retry & alerts | Retry failed deliveries (max 3 attempts); alert officer when a party cannot be reached | Make.com | Scenario 3 live |  | Not started |  | NEW
| Week 8 | Admin digest summary | Daily/weekly summary email to admin/head on notices sent / failed | Make.com, Email | Summary email scenario |  | Not started | Optional but recommended
Phase 5: Polish & Launch | Week 8 | Final security review | Re-run RLS tests; check storage bucket is private, webhook secret, service key storage, audit log coverage | Supabase RLS | Security audit passed |  | Not started | RLS itself is built & tested in Week 2 | CHANGED — scope
| Week 9 | Data migration | Import existing cases, parties, hearings; reconcile counts against old system | Supabase, scripts | Legacy data live in new app |  | Not started | Mapping from Week 0 | NEW
| Week 9 | MIS/monthly report | Auto month-end MIS: received, closed (by closed_at), carried forward | Supabase views, Next.js | MIS report page/export |  | Not started | Depends on closed_at column | CHANGED
| Week 9 | Staff/RBAC management UI | Admin screen to add/edit/deactivate staff and roles (admin/staff) | Next.js, Supabase Auth | Staff Management screen |  | Not started | Deactivate, don't delete — keeps case history | CHANGED
| Week 9 | Backups & monitoring | Enable daily backups / PITR; error logging for API routes and Make.com failures | Supabase, Vercel | Restore tested once |  | Not started |  | NEW
| Week 10 | UAT & bug fixing | User acceptance testing with real cases, fix issues | - | Stable release candidate |  | Not started
| Week 10 | Production deploy | Final Vercel production deploy, domain setup, go-live | Vercel | Live production app |  | Not started

## Screens
Screens / Pages to Build (v2)
Every page, its purpose, and who can access it. Row colours: green = NEW in v2 · yellow = CHANGED/MOVED · red strikethrough = REMOVED (see Change Log tab)
Screen | Purpose | Key Fields / Actions | Access Role | Reference | v2 Change
Login | Officer/admin authentication | Email + password or magic link | All users | Supabase Auth
Dashboard | Act/Section-wise stats: Total / Closed / Open / Forwarded | Per-Act cards, click-through to filtered case list; failed-delivery count | All users (scoped) | tapace.com Dashboard | CHANGED — failed deliveries
Case List (Forms Management) | Browse & search all cases | File Number, Applicant, Management, Next Hearing columns; Advanced Filters panel | All users (scoped) | tapace.com Forms Management System
Advanced Filters | Narrow case list | Search by file number, Act, Section, Receive From, hearing date range | All users | tapace.com Advanced Filters | CHANGED — Act filter
Create Current Entry | Add a new case | File Number, Act, Received Date, Memo Number, Subject, Received From, Section (auto-assigned to creator if staff) | Staff/Admin | tapace.com Create Current Entry | CHANGED
Case Details | Full case view | Basic Info, Applicant Details, Management Details, Case Information, Hearing history, Status history, Print Notice / Download DOCX | All users (scoped) | tapace.com Form Details | CHANGED — hearing & status history
Case Edit | Update case fields, remarks, status | Received From, Section, Remarks (date+text+URL), Status (+ Forwarded To), Amount | Staff/Admin | tapace.com edit form | CHANGED — hearing moved to Hearings
Hearings | Schedule & track hearings for a case | Add / reschedule / mark held or adjourned, outcome notes | Staff/Admin (scoped) | New | NEW
Notice Generator | Generate & send notice for a case | Template picker, hearing picker, preview, recipients check, Generate & Send button | Staff/Admin | New — triggers Make.com | CHANGED
Notice History | Track sent notices per case | Per notice: each party × channel status (pending/sent/delivered/failed), timestamp, error, Retry button | All users (scoped) | New | CHANGED — per delivery + retry
Notice Templates | Manage DOCX templates and linked WhatsApp template names | Upload DOCX, notice type, language, WhatsApp template name, active on/off | Admin | New | NEW
Section Management | Manage Section lookup list | Add/Delete section names | Admin | tapace.com Section Management
Receive Management | Manage Received-From lookup list | Add/Delete receive-from entries | Admin | tapace.com Receive Management
Staff Management | Manage officers/users | Add Staff, edit role (admin/staff), deactivate | Admin | tapace.com Staff Management | CHANGED — role names, deactivate
Monthly MIS Report | Month-end summary | Received / Closed / Carried Forward, per Act & section, exportable | Admin (Head) | New — per portal MIS requirement
Data Import | One-time load of legacy cases | Upload Excel/CSV, preview mapping, validation errors, import | Admin | New | NEW
Audit Log | See who changed what | Filter by case, user, date | Admin | New | NEW

## Data Model
Supabase Database Schema (v2)
Tables, columns, types, and notes. Row colours: green = NEW in v2 · yellow = CHANGED/MOVED · red strikethrough = REMOVED (see Change Log tab)
Table | Column | Type | Notes | v2 Change
cases | id | uuid (pk)
| office_code | text | unique (office_code, file_number) — confirm if multi-office | NEW
| file_number | text | unique per office
| act | text | EC / ID / S&E / … — kept separate from section | NEW
| section_id | uuid (fk -> sections)
| received_from_id | uuid (fk -> received_from)
| received_date | date
| next_hearing_date | date | kept in sync from hearings (earliest scheduled) | CHANGED
| status | text | open / closed / forwarded
| forwarded_to | text | nullable; set when status = forwarded | NEW
| closed_at | date | nullable; needed for MIS closed / carried forward | NEW
| subject | text
| memo_number | text | nullable
| amount_recovered | numeric | nullable
| assigned_officer_id | uuid (fk -> profiles) | for RBAC scoping; defaults to creator when staff creates | CHANGED
| created_by | uuid (fk -> profiles) |  | NEW
| created_at | timestamptz | default now()
| updated_at | timestamptz | trigger-maintained | NEW
| deleted_at | timestamptz | nullable; soft delete | NEW
parties | id | uuid (pk)
| case_id | uuid (fk -> cases)
| role | text | applicant / management
| name | text
| phone | text[] | supports multiple numbers
| whatsapp_phone | text | nullable; E.164 (+91…) number used for WhatsApp | NEW
| email | text | nullable
| address | text | nullable
| preferred_language | text | te / en; only if bilingual notices adopted | NEW
hearings | id | uuid (pk) |  | NEW
| case_id | uuid (fk -> cases) |  | NEW
| hearing_date | date |  | NEW
| hearing_time | time | nullable | NEW
| status | text | scheduled / held / adjourned / cancelled | NEW
| outcome_notes | text | nullable | NEW
| created_at | timestamptz | default now() | NEW
notices | id | uuid (pk)
| case_id | uuid (fk -> cases)
| hearing_id | uuid (fk -> hearings) | nullable; links hearing notices to the hearing | NEW
| template_id | uuid (fk -> notice_templates) |  | NEW
| type | text | hearing / show_cause / closure / order
| doc_path | text | path in private Storage bucket; signed URL made at send time | CHANGED — was doc_url
| generated_at | timestamptz
| generated_by | uuid (fk -> profiles) | null when created by batch scenario | NEW
| status | text | pending / partial / sent / failed — rolled up from notice_deliveries | CHANGED — was sent_status
| idempotency_key | text (unique) | stops duplicate notices, e.g. hearing_id + type | NEW
| sent_at | timestamptz | moved to notice_deliveries | REMOVED
| channel | text | moved to notice_deliveries | REMOVED
notice_deliveries | id | uuid (pk) | one row per party × channel | NEW
| notice_id | uuid (fk -> notices) | unique (notice_id, party_id, channel) | NEW
| party_id | uuid (fk -> parties) |  | NEW
| channel | text | email / whatsapp | NEW
| recipient | text | email address or phone actually used | NEW
| status | text | pending / sent / delivered / read / failed | NEW
| provider_message_id | text | nullable; proof of service | NEW
| error | text | nullable | NEW
| attempt_count | int | default 0; retry stops at 3 | NEW
| sent_at | timestamptz | nullable | NEW
| updated_at | timestamptz |  | NEW
notice_templates | id | uuid (pk) |  | NEW
| name | text |  | NEW
| notice_type | text | hearing / show_cause / closure / order | NEW
| language | text | te / en | NEW
| docx_path | text | Storage path of DOCX template | NEW
| whatsapp_template_name | text | Meta-approved template name | NEW
| active | boolean | default true | NEW
remarks | id | uuid (pk)
| case_id | uuid (fk -> cases)
| date | date
| text | text
| url | text | nullable, supporting link
| created_by | uuid (fk -> profiles) |  | NEW
case_status_history | id | uuid (pk) |  | NEW
| case_id | uuid (fk -> cases) |  | NEW
| from_status | text |  | NEW
| to_status | text |  | NEW
| changed_by | uuid (fk -> profiles) |  | NEW
| changed_at | timestamptz | default now() | NEW
| note | text | nullable | NEW
sections | id | uuid (pk)
| name | text | e.g. JM, Administration (Act now in cases.act) | CHANGED
received_from | id | uuid (pk)
| name | text | e.g. DCL Rangareddy, JCL RR
profiles | id | uuid (pk, fk -> auth.users)
| role | text | admin / staff (same labels on Staff Management screen) | CHANGED
| full_name | text
| email | text
| active | boolean | default true; deactivate instead of delete | NEW
audit_log | id | bigint (pk) | written by triggers on cases, parties, hearings, notices | NEW
| table_name | text |  | NEW
| record_id | uuid |  | NEW
| action | text | insert / update / delete | NEW
| changed_by | uuid |  | NEW
| changed_at | timestamptz | default now() | NEW
| diff | jsonb | old vs new values | NEW

## RBAC Matrix
Role-Based Access Matrix (v2)
Who can do what. Row colours: green = NEW in v2 · yellow = CHANGED/MOVED · red strikethrough = REMOVED (see Change Log tab)
Feature / Screen | Admin (Head) | Staff (Officer) | Notes | v2 Change
View all cases | Yes | No — own cases only | RLS policy filters by assigned_officer_id; child tables join to cases | CHANGED — child tables
Create case | Yes | Yes | Staff-created case auto-assigned to creator | CHANGED
Edit case | Yes | Yes — own cases only
Delete case | Yes (soft delete) | No | Sets deleted_at; row kept for audit | CHANGED
Schedule / update hearings | Yes | Yes — own cases only |  | NEW
Generate & send notice | Yes | Yes — own cases only | Triggers Make.com webhook
Retry failed delivery | Yes | Yes — own cases only |  | NEW
View notice history | Yes — all | Yes — own cases only
Manage notice templates | Yes | No |  | NEW
Manage Sections | Yes | No
Manage Received From | Yes | No
Manage Staff / Roles | Yes | No | Deactivate instead of delete
View Dashboard stats | Yes — all sections | Yes — own cases only
View Monthly MIS | Yes | OPEN DECISION: No, or own-scope summary only | Decide before Week 9 | CHANGED — flagged as open
Import legacy data | Yes | No | One-time, Week 9 | NEW
View audit log | Yes | No |  | NEW

## Automation
Make.com Automation Scenarios (v2)
Notice delivery to both parties — Email + WhatsApp. Row colours: green = NEW in v2 · yellow = CHANGED/MOVED · red strikethrough = REMOVED (see Change Log tab)
Scenario | Trigger | Steps (Modules) | Sends To | Writeback | v2 Change
1. Immediate Notify | Webhook fired the moment a notice is generated in the app | 1) Webhook receives {notice_id, case_id, hearing_id, notice_type, signed doc_url, applicant, management, whatsapp_template_name} with shared-secret header 2) Filter: reject if secret header wrong 3) Router splits into Applicant branch and Management branch 4) Each branch: Email module (doc link/attachment) + WhatsApp module (approved template with document header) 5) After each send: HTTP PATCH notice_deliveries row (status, provider_message_id, error) | Applicant + Management (both parties, same notice) | notice_deliveries per party × channel; notices.status rolled up by DB trigger | CHANGED — secret, per-delivery writeback
2. Batch/Scheduled Notify | Daily schedule (e.g. 9:00 AM IST) | 1) Scheduler trigger 2) HTTP call to Supabase Edge Function: hearings in next N days with no sent notice for that hearing_id 3) Iterator over hearings 4) Per hearing: call notice generation API (idempotency_key = hearing_id + 'hearing') — creates doc + delivery rows 5) Email + WhatsApp to both parties (same as Scenario 1) 6) Writeback per delivery 7) Optional: one summary email to Admin/Head (sent / failed counts) | Applicant + Management for every due hearing | notice_deliveries updated per delivery; optional admin digest email | CHANGED — generates notice, dedupe
3. Retry Failed | Daily schedule (e.g. 2:00 PM IST) or Retry button | 1) Fetch notice_deliveries with status = failed and attempt_count < 3 2) Resend on same channel with fresh signed URL 3) Writeback, attempt_count + 1 4) After 3rd failure: email assigned officer to serve by post / hand | Only the party + channel that failed | notice_deliveries.status, attempt_count | NEW
Rules & notes
• No double-sends: notices.idempotency_key and unique (notice_id, party_id, channel) mean Scenario 1 and 2 cannot notify the same hearing twice.
• WhatsApp: needs a Business API provider (Gupshup / 360dialog / Twilio) connected in Make.com, Meta business verification, and pre-approved templates for every notice type. Plain Make.com has no native WhatsApp module.
• Security: webhook protected by a shared secret header; the Supabase service_role key lives only in Make.com connection / Vercel env vars; notices stored in a private bucket and sent as signed URLs (e.g. 7-day expiry).
• Proof of service: keep provider_message_id and delivered/read statuses — useful if a party says they never received the notice.
• Cost estimate: ~10 Make.com operations per notice (webhook, router, 4 sends, 4 writebacks). 50 notices/day ≈ 11,000 ops/month → paid Make.com plan needed. Alternative: Supabase pg_cron + Edge Functions calling provider APIs directly (no per-operation cost).

## Setup Checklist
One-Time Setup Checklist (v2)
Ordered by when it is needed. Row colours: green = NEW in v2 · yellow = CHANGED/MOVED · red strikethrough = REMOVED (see Change Log tab)
# | Setup Item | Where | Needed by | Done? | v2 Change
1 | Sign up with a WhatsApp Business API provider (Gupshup / 360dialog / Twilio) | chosen provider | Week 0 — start now |  | MOVED up — long lead
2 | Complete Meta Business verification for the department | Meta Business Manager | Week 0 — start now |  | NEW
3 | Submit WhatsApp message templates (one per notice type) for approval | provider / Meta | Week 0 |  | NEW
4 | Prepare notice/letter templates (letterhead, wording) for DOCX generation; decide Telugu/English | Word/Google Docs | Week 0 |  | CHANGED — language decision
5 | Export existing case data from tapace.com / Excel for migration | tapace.com / Excel | Week 0 |  | NEW
6 | Assign an Owner to every Roadmap task | This workbook | Week 0 |  | NEW
7 | Create Vercel account & new project | vercel.com | Week 1
8 | Create Supabase projects — dev and prod (get URL + API keys) | supabase.com | Week 1 |  | CHANGED — dev + prod
9 | Create Make.com account; choose plan against ~11k ops/month estimate | make.com | Week 1 |  | CHANGED — plan sizing
10 | Prepare officer list (names, emails, roles admin/staff) for Staff Management setup | Excel/HR list | Week 1
11 | Confirm Act, Section and Received-From master lists to pre-load | This workbook / existing data | Week 2 |  | CHANGED — Act list
12 | Connect Make.com to that WhatsApp provider | Make.com > Connections | Week 5
13 | Connect Make.com to an Email sending service; set up SPF/DKIM on sending domain | Make.com > Connections, DNS | Week 5 |  | CHANGED — deliverability
14 | Generate webhook shared secret; store in Vercel env vars and Make.com | Vercel, Make.com | Week 6 |  | NEW
15 | Decide domain name for the live app | Vercel > Domains | Week 9
16 | Decide: staff access to MIS; PDF vs DOCX; single vs multi-office file numbers | Admin / Head | Before Week 5 |  | NEW

## Change Log
Change Log — v1 → v2
Revised 27 Sep 2026. Original: Labour_Portal_Full_Development_Plan_v1_backup.xlsx
Tab | Change | Why
Data Model | Added notice_deliveries (one row per party × channel); removed notices.sent_at / channel | A single sent_status could not record e.g. 'applicant email sent, management WhatsApp failed'; provider IDs give proof of service
| Added hearings table; next_hearing_date now synced from it | Overwriting one date lost hearing history, and the batch could not tell which hearing a notice was for
| Added cases.closed_at and case_status_history | Monthly MIS (closed / carried forward) cannot be computed from status alone
| Added deleted_at, forwarded_to, act, office_code, created_by, updated_at | Soft delete (RBAC tab), forwarded cases, per-Act dashboard and per-office file numbers were referenced but had no columns
| Added notice_templates, audit_log, parties.whatsapp_phone, profiles.active | Template picker needs a table; accountability; WhatsApp needs one E.164 number; deactivate instead of deleting staff
| Role labels unified to admin / staff | Staff Management screen said admin/user
Roadmap | New Phase 0 (Week 0): WhatsApp verification + template approval, notice templates, migration scoping | WhatsApp approval takes days–weeks and blocked Week 6; templates blocked Week 5
| RLS moved from Week 1 to Week 2 with automated tests | Policies depend on cases.assigned_officer_id, created in Week 2; security should be tested from the start, not only in Week 8
| New tasks: Hearings, data migration, retry of failed deliveries, backups & monitoring | Were missing from v1
| Added 'v2 Change' column and Status dropdown | Traceability and tracking
Automation | Webhook shared secret, idempotency key, per-delivery writeback, Scenario 3 retry | Prevents spoofed calls and double-sends; failures are visible and retried
| Batch scenario now generates the notice document before sending | v1 batch had no notice/document to send
| Added Make.com cost estimate and Supabase-only alternative | ~11k ops/month at 50 notices/day exceeds the free plan
Screens / RBAC | Added Hearings, Notice Templates, Data Import, Audit Log screens and permissions | Match the new tables and tasks
Setup Checklist | Reordered by 'Needed by'; added Meta verification, template approval, data export, webhook secret, owners, open decisions | Long-lead items first
Still open | Owner column is empty; MIS visibility for staff, Telugu notices, PDF output and multi-office numbering undecided | Need a decision from the Head / Admin