## Overview
Labour Case Management Web App — Development Master Plan
Fresh build, inspired by tapace.com, for case notices + automated party notifications
Item | Detail
Purpose | Internal web app to manage Labour Department case files (EC/ID/S&E/etc.), track hearings, generate notices, and auto-notify both applicant and management by Email + WhatsApp
Frontend | Next.js, hosted on Vercel
Backend / Database | Supabase — Postgres database, Auth (login/roles), Storage (uploaded docs & generated notices)
Automation | Make.com — two scenarios: (1) Immediate notify on notice creation, (2) Daily/batch scheduled notify for upcoming hearings
Notification channels | Email and WhatsApp (WhatsApp requires a Business API provider such as Gupshup / 360dialog / Twilio connected in Make.com)
Reference UI | tapace.com screens: Form Details, Receive Management, Section Management, Staff Management, Advanced Filters, Create Current Entry
Core users | Admin (full access) and Staff/Officers (assigned cases only) via role-based access
How to use this file | Roadmap tab = week-by-week build plan · Screens tab = every page to build · Data Model tab = database tables · RBAC tab = who can do what · Automation tab = the two Make.com scenarios in detail · Checklist tab = one-time setup steps before coding starts

## Roadmap
Development Roadmap
10-week plan, phase by phase
Phase | Week | Task | Description | Tech/Tool | Deliverable | Owner | Status | Notes
Phase 1: Foundation | Week 1 | Project setup | Initialize Next.js app, connect to Vercel, set up Supabase project | Next.js, Vercel, Supabase | Deployed skeleton app on Vercel |  | Not started | Create separate dev/prod Supabase projects
| Week 1 | Auth & RBAC | Supabase Auth (email/magic link), roles table (admin/staff), RLS policies | Supabase Auth, RLS | Login working with role-based access |  | Not started | Admin = full access, Staff = own cases only
| Week 2 | Core database schema | Tables: cases, parties, sections, received_from, staff/profiles | Supabase Postgres | Schema deployed with relationships |  | Not started | See Data Model tab
| Week 2 | Admin lookup management | CRUD UI for Sections and Received-From lists | Next.js, Supabase | Section & Receive Management screens |  | Not started | Matches existing tapace.com pattern
Phase 2: Case Management | Week 3 | Case CRUD | Create/view/edit case: file number, dates, status, subject | Next.js, Supabase | Case list + case detail page |  | Not started
| Week 3 | Applicant & Management details | Sub-forms for both parties: name, phone(s), email, address | Next.js, Supabase | Parties linked to case |  | Not started | Supports multiple phone numbers
| Week 4 | Filters & search | Filter by file number, section, receive-from, hearing date range | Next.js, Supabase | Advanced Filters screen |  | Not started
| Week 4 | Dashboard stats | Section-wise Total/Closed/Open/Forwarded counts | Supabase views/RPC | Stats dashboard per Act/Section |  | Not started
Phase 3: Notices & Documents | Week 5 | DOCX/PDF template engine | Templated notice/order generation from case data | docxtemplater or similar, Supabase Storage | Print Notice / Download DOCX feature |  | Not started | Letterhead + case fields populated
| Week 5 | Notice tracking table | notices table: type, doc_url, sent_status, channel, timestamps | Supabase Postgres | Notice history per case |  | Not started
| Week 6 | Notice generation API route | API route builds doc, uploads to Storage, fires webhook | Next.js API route / Edge Function | Working generate-and-notify endpoint |  | Not started | Payload: case_id, parties, doc_url, notice_type
Phase 4: Automation (Make.com) | Week 6 | Immediate notify scenario | Webhook-triggered scenario: Email + WhatsApp to both parties | Make.com, Email, WhatsApp Business API | Scenario 1 live and tested |  | Not started | Needs WhatsApp API provider
| Week 7 | Batch notify scenario | Scheduled scenario: query due notices, iterate, send in bulk | Make.com scheduler, Supabase REST/Edge Function | Scenario 2 live and tested |  | Not started | Daily run, e.g. 9 AM IST
| Week 7 | Delivery status writeback | Make.com updates notices.sent_status back to Supabase | Make.com HTTP module, Supabase REST API | Sent/Pending/Failed visible in dashboard |  | Not started
| Week 8 | Admin digest summary | Daily/weekly summary email to admin/head on notices sent | Make.com, Email | Summary email scenario |  | Not started | Optional but recommended
Phase 5: Polish & Launch | Week 8 | RLS & security review | Verify officers only see assigned cases; admin sees all | Supabase RLS | Security audit passed |  | Not started
| Week 9 | MIS/monthly report | Auto month-end MIS: received, closed, carried forward | Supabase views, Next.js | MIS report page/export |  | Not started
| Week 9 | Staff/RBAC management UI | Admin screen to add/edit/remove staff and roles | Next.js, Supabase Auth | Staff Management screen |  | Not started
| Week 10 | UAT & bug fixing | User acceptance testing with real cases, fix issues | - | Stable release candidate |  | Not started
| Week 10 | Production deploy | Final Vercel production deploy, domain setup, go-live | Vercel | Live production app |  | Not started

## Screens
Screens / Pages to Build
Every page, its purpose, and who can access it
Screen | Purpose | Key Fields / Actions | Access Role | Reference
Login | Officer/admin authentication | Email + password or magic link | All users | Supabase Auth
Dashboard | Section-wise stats: Total / Closed / Open / Forwarded | Per-Act cards, click-through to filtered case list | All users (scoped) | tapace.com Dashboard
Case List (Forms Management) | Browse & search all cases | File Number, Applicant, Management columns; Advanced Filters panel | All users (scoped) | tapace.com Forms Management System
Advanced Filters | Narrow case list | Search by file number, Section dropdown, Receive From dropdown, hearing date range | All users | tapace.com Advanced Filters
Create Current Entry | Add a new case | File Number, Received Date, Memo Number, Subject, Received From, Section | Staff/Admin | tapace.com Create Current Entry
Case Details | Full case view | Basic Info, Applicant Details, Management Details, Case Information, Print Notice / Download DOCX | All users (scoped) | tapace.com Form Details
Case Edit | Update case fields, remarks, hearing date, status | Received From, Section, Remarks (date+text+URL), Next Hearing Date, Final Status, Amount | Staff/Admin | tapace.com edit form
Notice Generator | Generate & send notice for a case | Template picker, preview, Generate & Send button | Staff/Admin | New — triggers Make.com
Notice History | Track sent notices per case | Type, Channel (Email/WhatsApp), Sent Status, Timestamp | All users (scoped) | New
Section Management | Manage Section lookup list | Add/Delete section names | Admin | tapace.com Section Management
Receive Management | Manage Received-From lookup list | Add/Delete receive-from entries | Admin | tapace.com Receive Management
Staff Management | Manage officers/users | Add Staff, edit role (admin/user), delete | Admin | tapace.com Staff Management
Monthly MIS Report | Month-end summary | Received / Closed / Carried Forward, per section, exportable | Admin (Head) | New — per portal MIS requirement

## Data Model
Supabase Database Schema
Tables, columns, types, and notes
Table | Column | Type | Notes
cases | id | uuid (pk)
| file_number | text | unique per office
| section_id | uuid (fk -> sections)
| received_from_id | uuid (fk -> received_from)
| received_date | date
| next_hearing_date | date
| status | text | open / closed / forwarded
| subject | text
| memo_number | text | nullable
| amount_recovered | numeric | nullable
| assigned_officer_id | uuid (fk -> profiles) | for RBAC scoping
| created_at | timestamptz | default now()
parties | id | uuid (pk)
| case_id | uuid (fk -> cases)
| role | text | applicant / management
| name | text
| phone | text[] | supports multiple numbers
| email | text | nullable
| address | text | nullable
notices | id | uuid (pk)
| case_id | uuid (fk -> cases)
| type | text | hearing / show_cause / closure / order
| doc_url | text | Supabase Storage URL
| generated_at | timestamptz
| sent_status | text | pending / sent / failed
| sent_at | timestamptz | nullable
| channel | text | email / whatsapp / both
remarks | id | uuid (pk)
| case_id | uuid (fk -> cases)
| date | date
| text | text
| url | text | nullable, supporting link
sections | id | uuid (pk)
| name | text | e.g. JM, EC, Administration
received_from | id | uuid (pk)
| name | text | e.g. DCL Rangareddy, JCL RR
profiles | id | uuid (pk, fk -> auth.users)
| role | text | admin / staff
| full_name | text
| email | text

## RBAC Matrix
Role-Based Access Matrix
Who can do what
Feature / Screen | Admin (Head) | Staff (Officer) | Notes
View all cases | Yes | No — own cases only | RLS policy filters by assigned_officer_id
Create case | Yes | Yes
Edit case | Yes | Yes — own cases only
Delete case | Yes | No | Soft-delete recommended, not hard delete
Generate & send notice | Yes | Yes — own cases only | Triggers Make.com webhook
View notice history | Yes — all | Yes — own cases only
Manage Sections | Yes | No
Manage Received From | Yes | No
Manage Staff / Roles | Yes | No
View Dashboard stats | Yes — all sections | Yes — own cases only
View Monthly MIS | Yes | No (or own-scope summary only) | Decide if staff see their own MIS slice

## Automation
Make.com Automation Scenarios
Notice delivery to both parties — Email + WhatsApp
Scenario | Trigger | Steps (Modules) | Sends To | Writeback
1. Immediate Notify | Webhook fired the moment a notice is generated in the app | 1) Webhook receives {case_id, notice_type, doc_url, applicant, management} 2) Router splits into Applicant branch and Management branch 3) Each branch: Email module (send doc link/attachment) + WhatsApp module (via Business API connector) 4) HTTP module PATCHes Supabase notices row | Applicant + Management (both parties, same notice) | notices.sent_status = 'sent', sent_at = now()
2. Batch/Scheduled Notify | Daily schedule (e.g. 9:00 AM IST) | 1) Scheduler trigger 2) HTTP GET to Supabase (or Edge Function) — all cases with next_hearing_date in next N days, not yet notified 3) Iterator over returned case list 4) Per case: Email + WhatsApp to both parties (same as Scenario 1) 5) HTTP writeback per case 6) Optional: one summary email to Admin/Head listing count sent | Applicant + Management for every due case in the batch | notices.sent_status updated per case; optional admin digest email
Note: WhatsApp sending needs a WhatsApp Business API provider (e.g. Gupshup, 360dialog, or Twilio) connected as a Make.com app/connection. Plain Make.com has no native WhatsApp module without one of these providers.

## Setup Checklist
One-Time Setup Checklist
Do these before development starts
# | Setup Item | Where | Done?
1 | Create Vercel account & new project | vercel.com
2 | Create Supabase project (get URL + API keys) | supabase.com
3 | Create Make.com account | make.com
4 | Sign up with a WhatsApp Business API provider (Gupshup / 360dialog / Twilio) | chosen provider
5 | Connect Make.com to that WhatsApp provider | Make.com > Connections
6 | Connect Make.com to an Email sending service (Gmail/SendGrid/etc.) | Make.com > Connections
7 | Decide domain name for the live app | Vercel > Domains
8 | Prepare notice/letter templates (letterhead, wording) for DOCX generation | Word/Google Docs
9 | Prepare officer list (names, emails, roles) for Staff Management setup | Excel/HR list
10 | Confirm Section and Received-From master lists to pre-load | This workbook / existing data